## Sheet1
Task | Duration | Start Date | End Date | Assignees | Completion Status
#1.0 - Project Management | 2 days | 2023-11-01 | 2023-11-02 | Naga Prasath Saravanan | 100%
1.1 - Background Research | 1 day | 2023-11-01 | 2023-11-01 | Full Team | 100%
1.2 - Project Plan | 1 day | 2023-11-02 | 2023-11-02 | Naga Prasath Saravanan, Sufyan Khan, Rahul Nagaraju | 100%
2.0 - Building the Application | 6 days | 2023-11-03 | 2023-11-10 | Josh Reginaldo Brahmantya Wardhana Abhishek Deshpande | 100%
2.1 - Research on APIs | 1 day | 2023-11-03 | 2023-11-03 | Josh Reginaldo Brahmantya Wardhana Abhishek Deshpande | 100%
2.2 - Create user main menu | 1 day | 2023-11-06 | 2023-11-06 | Josh Reginaldo Brahmantya Wardhana Abhishek Deshpande | 100%
2.3 - Add specific data entry forms for each API | 1 day | 2023-11-07 | 2023-11-07 | Josh Reginaldo Brahmantya Wardhana Abhishek Deshpande | 100%
2.4 - Send User values to the API and receive a response | 2 days | 2023-11-08 | 2023-11-09 | Josh Reginaldo Brahmantya Wardhana Abhishek Deshpande | 100%
2.5 - Format API response to display on the GUI | 1 day | 2023-11-10 | 2023-11-10 | Josh Reginaldo Brahmantya Wardhana Abhishek Deshpande | 100%
3.0 - Testing the Application | 5 days | 2023-11-13 | 2023-11-17 | Full Team | 100%
4.0 - Collect Data from sources | 4 days | 2023-11-20 | 2023-11-23 | Kshiragna Challagulla | 100%
4.1 - Compiling the data | 1 day | 2023-11-20 | 2023-11-20 | Kshiragna Challagulla, Rahul Nagaraju | 100%
4.2 - Data Analysis | 2 day | 2023-11-21 | 2023-11-22 | Kshiragna Challagulla | 100%
4.3 - Key Findings | 1 day | 2023-11-23 | 2023-11-23 | Josh Reginaldo Brahmantya Wardhana Abhishek Deshpande, Kshiragna Challagulla | 100%
5.0 - Documentation | 5 day | 2023-11-24 | 2023-11-30 | Naga Prasath, Sufyan, Rahul Nagaraju, Josh Reginaldo | 100%
5.1 Test Document | 1 day | 11//24/2023 | 2023-11-24 | Naga Prasath, Sufyan, Rahul Nagaraju, Josh Reginaldo | 100%
5.2 - Project Management Plan | 1 day | 2023-11-25 | 2023-11-25 | Naga Prasath Saravanan | 100%
5.3 - Earned Value Management | 1 day | 2023-11-27 | 2023-11-27 | Rahul Nagaraju | 100%
5.4- Risk Management Plan | 1 day | 2023-11-28 | 2023-11-28 | Naga Prasath Saravanan, Sufyan Khan, Rahul Nagaraju | 100%
5.5 - Project Report | 2 days | 2023-11-28 | 2023-11-29 | Sufyan Khan, Rahul Nagaraju | 100%
5.6 - Final Presentation | 2 days | 2023-11-29 | 2023-11-30 | Full Team | 100%