## Sheet1
RISK MANAGEMENT LOG
Project Name: |  |  | OSINT App Project
National Center: |  |  | IIT
Project Manager Name: |  |  | Sufyan Khan, Rahul Nagaraju, Prasath Saravanan
Project Description: |  |  | OSINT
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy
1 | Open | Low | Low | Green | Difficulty in virtual communication | Confusion in task allocation due to communication issues | Project Resources, Schedule | Delayed responses, unclear of whose job is what | Lack of synchronous communication | Mitigation | Continue using the chosen communication application
2 | Open | Medium | Low | Green | Missed meeting scheduling affecting project schedule | Potential restriction in achieving project goal | Schedule | Difficulty in finding a common meeting time | Varied availability of team members | Acceptance | Schedule meetings well in advance
3 | Open | Low | Low | Green | Miscalculated budget analysis leading to overspending or insufficient profits | Hinders project goal achievement | Project Resources, Budget | Budget overruns or shortages | Lack of accurate budget planning | Mitigation | No further budget changes for now
4 | Open | Medium | Medium | Yellow | Time allocation to each task | Hinders project quality | Quality | Difficulty in acheiving excellence | Lack of enough time | Mitigation | Allocate more time
5 | Open | High | Low | Yellow | Software program failure | Potential project failure if the script doesn't open | Project Resources | Failure to open or display errors | incorrect code | Avoidance | Continuous bug fixing and updates check
6 | Open | High | Low | Yellow | Scripts not loading successfully on different systems | Incomplete project if scripts fail to load across platforms | Project Resources | Failure to load on various platforms | Incorrect code | Mitigation | Continuous testing across various platforms
7 | Open | Medium | Low | Green | Failure to accomplish project deliverables by the deadline | Potential project failure due to inefficient deliverables | Project Resources, Budget, Schedule | Lack of progress and lack of communication | Insufficient motivation or confusion in task instructions | Avoidance | Keep team updated on tasks and deadlines